## Incomplete Content Areas
Priority | Notes | Content Area | JIRA | Target Quarter | SKG Migration Status | SKG Notes | API Dev Status | API Notes | Source Document
3 | 2026-03-18 | Remaining Global Distribute - MedGuide | RX-2768 | 26.Q3 | In Progress | MedGuide content not yet in SKG. | Not Started | New EHRC MedGuide API required. Contract below RX-2113. Assigned: Minakshi. | Multum SKG Content Areas Priority List; 26Q3 Priorities
2 | 2026-04-15 | Remaining Global Distribute - Labels | RX-2768 | 26.Q3 / 26.Q4 | In Progress | Labels content not yet in SKG. | Not Started | New EHRC Labels API required. Contract TBD with Aimee. Assigned: Minakshi. | Multum SKG Content Areas Priority List; 26Q3 Priorities
4 |  | Remaining Global Distribute - Manufacturer Ordered Drug Names | RX-2768 | 26.Q3 | Not Started | Not yet in SKG. | Not Required |  | Multum SKG Content Areas Priority List
5 |  | Medication Order Sentences | RX-9208 | 26.Q3 | Not Started | Not yet in SKG. No consumers yet in Q3. | Not Required | No API defined. No consumers yet. | Multum SKG Content Areas Priority List; 26Q3 Priorities
6 |  | References / Citations | RX-2768 | 26.Q3 | Not Started | References content not yet moved to SKG. | Not Started | 3 new EHRC services required: GetAllergyReferences, GetDrugDiseaseInteractionReferences, GetDrugInteractionReferences. | Multum SKG Content Areas Priority List; 26Q3 Priorities
WC | New Graph | Lexicomp Pediatric DRC | RX-7005 | 26.Q3 | On Hold | Requires separate restricted model for licensed customers. | On Hold | EHRC API defined. ON HOLD pending license model. Assigned: Sudatta. | Multum SKG Content Areas Priority List; 26Q3 Priorities
WC | New Graph | IV Compatibility (Kings Guide) | RX-2064 | 26.Q1 / 26.Q2 | On Hold | Additional IV compatibility content (Y-site?) still needs to move. Confirm with Chandra/Megan. | On Hold | New EHRC service required. ON HOLD - Millennium pushed to Q4/Q127. ORDERS-17805 dependency. MB to test prior to GA. | Multum SKG Content Areas Priority List; 26Q3 Priorities
Pipeline Team | Project | Automate Content Deployment to SKG | RX-8927 | 26.Q3 | In Progress | Manual TTL deployment weekly as interim. Raghu team owns automation. Assigned: Madhulika/Sai. | N/A | Infrastructure effort, not a content API. | 26Q3 Priorities
-> |  | Medical Supplies |  |  |  |  | On Hold
1 |  | Content Up to Date
Manual - Interim
- Files (Drug Images) - Coordinate w/ Poojan
- PEL - Coordinate w/ Poojan
| Weeks Est | Area
| 4 | RDF
| 4 | TEST
| 3 | DEPLOY SKG - Data Migration
Content SKG
Other Content
MCS? - On-Hold
SKG Assumes - GUID for a particular concept (generic concept)
Country Specific - Unique identifiers
Split DNUM - d0001 - should be same in all countries
France BCB
Timeline | Q4 | CA + SA

## Complete List of "Incomplete"
Priority | Content Area | JIRA | Target Quarter | Michael's Status | SKG Migration Status | SKG Notes | API Dev Status | API Notes | Source Document
1 | Map Multum to Standards (Frequency / Route / Dose Form) | RX-2402 | 26.Q1 | Complete | In Progress | 25.10: UOM + Condition complete. Frequency, route, dose form to SNOMED outstanding. | Not Required |  | Multum SKG Content Areas Priority List
2 | Therapeutic Categories | RX-1246 | 26.Q1 | Complete | Complete | Available in SKG since 25.10 via NDC Search feature. | Not Started | New EHRC Therapeutic Category service required (RX-13557). Replaces MCS TC commands. 7 use cases defined. | Multum SKG Content Areas Priority List; 26Q3 Priorities
2 | Therapeutic Duplicate Categories | RX-13524 | 26.Q3 | Complete | Complete | Content available in SKG. | In Progress | New Therapeutic Duplicate EHRC API for mCDS team. Assigned: Aman/Sudatta. | Multum SKG Content Areas Priority List; 26Q3 Priorities
3 | Multum to CVX Cross Mappings (MVX / new dates) | RX-1297 | 26.Q2 | Complete | In Progress | Base CVX complete 25.10. New start/end dates and MVX codes outstanding. | Complete | API live. | Multum SKG Content Areas Priority List
4 | Side Effects | RX-2129 | 26.Q1 (S&S) / Post-Feb 2026 (CK) | Complete | Complete | Clinical text content in SKG. | In Progress | EHRC API built. Clinical Knowledge Agent integration post-Feb 2026. | Multum SKG Content Areas Priority List
4 | Dosing (Flat Text / Additional Dosing) | RX-2129 | 26.Q1 (S&S) / Post-26.Q1 (CK) | Complete | Complete | Clinical text content in SKG. | In Progress | EHRC API built. CK agent integration post-26.Q1. | Multum SKG Content Areas Priority List
4 | Warnings (incl. Beers Criteria) | RX-2129 | 26.Q1 | Complete | Complete | Clinical text content in SKG. | In Progress | EHRC API built. S&S P1 integration outstanding. ORDERS-6043 (Beers) committed. | Multum SKG Content Areas Priority List
4 | Pharmacology | RX-2129 | 26.Q1 | Complete | Complete | Clinical text content in SKG. | In Progress | EHRC API built. ORDERS-6048 drug-genomics alerting open. | Multum SKG Content Areas Priority List
4 | Pharmacokinetics | RX-2129 | 26.Q1 | Complete | Complete | Clinical text content in SKG. | In Progress | EHRC API built. S&S consumer integration outstanding. | Multum SKG Content Areas Priority List
4 | Pregnancy / Lactation (S&S) | RX-2129 | 26.Q1 | Complete | Complete | Clinical text content in SKG. | In Progress | EHRC API built. S&S 26.Q1 consumer integration outstanding. | Multum SKG Content Areas Priority List
5 | Drug Condition Interactions | RX-2132 | 26.Q1 (S&S) / 26.Q3 (API) | Complete | Complete | Content in SKG. | In Progress | New Drug Condition EHRC API required for Orders (26.Q3). ORDERS-6039 open. | Multum SKG Content Areas Priority List; 26Q3 Priorities
5 | Drug Condition Management | RX-2132 | 26.Q1 | Complete | Complete | Content in SKG. | Not Started | New EHRC service needed for Orders med proposal. ORDERS-6041 open. | Multum SKG Content Areas Priority List
6 | Patient Education Leaflets - HTML with Icons | RX-2103 | 26.Q3 | Complete | Complete | Base PEL content in SKG. | In Progress | Existing PEL EHRC API update needed to support HTML with icons format. Assigned: Caleb. | Multum SKG Content Areas Priority List; 26Q3 Priorities
7 | IV Compatibility (Kings Guide) | RX-2064 | 26.Q1 / 26.Q2 | TBD | In Progress | Additional IV compatibility content (Y-site?) still needs to move. Confirm with Chandra/Megan. | On Hold | New EHRC service required. ON HOLD - Millennium pushed to Q4/Q127. ORDERS-17805 dependency. MB to test prior to GA. | Multum SKG Content Areas Priority List; 26Q3 Priorities
8 | Multum to SNOMED CT Cross Mappings (Allergy + Condition) | RX-2402 | 26.Q1 | Complete | Not Started | Allergy SNOMED and SNOMED Condition mappings not yet in SKG. | Not Required |  | Multum SKG Content Areas Priority List
9 | Drug Drug Interactions | RX-1216 | 26.Q1 (S&S P1) / Post-26.Q1 (CK) | Complete | Complete | Content in SKG. | Not Started | No EHRC API yet. S&S P1 and CK agent integration pending. | Multum SKG Content Areas Priority List
9 | Drug Food Interactions | RX-1216 | 26.Q1 | Complete | Complete | Included in Drug Drug Interactions migration. | Not Started | No EHRC API yet. Included in Drug Drug Interactions feature. | Multum SKG Content Areas Priority List
10 | Multum to RxNorm Cross Mappings | RX-2139 | 26.Q1 / 26.Q3 | Complete - Partial Implementation | Not Started | rxn_multum_map mappings at MMDC/DNUM/synonym level not yet in SKG. | Not Required |  | Multum SKG Content Areas Priority List
10 | References / Citations | RX-2768 | 26.Q3 | Not Started | Not Started | References content not yet moved to SKG. | Not Started | 3 new EHRC services required: GetAllergyReferences, GetDrugDiseaseInteractionReferences, GetDrugInteractionReferences. | Multum SKG Content Areas Priority List; 26Q3 Priorities
11 | Allergy Categories | RX-1216 | 26.Q1 | Not Started | Not Started | All allergy content including drug/allergy checking not yet in SKG. | Not Started | No EHRC API yet. | Multum SKG Content Areas Priority List
12 | Lexicomp Pediatric DRC | RX-7005 | 26.Q3 | On Hold | On Hold | Requires separate restricted model for licensed customers. | On Hold | EHRC API defined. ON HOLD pending license model. Assigned: Sudatta. | Multum SKG Content Areas Priority List; 26Q3 Priorities
12 | Morphine Milligram Equivalent (MME) | RX-2130 | 26.Q2 | Complete | In Progress | NOT in Global_Distribute. Separate pipeline required. | Not Started | No EHRC API defined yet. | Multum SKG Content Areas Priority List
13 | Filtered Order Sentences / RxBuilder KDMO | RX-1215 | 26.Q1 (content) / 26.Q3 (API) | Complete | Complete | Content in SKG. | In Progress | New RxBuilder EHRC API for Orders in progress. Orders not consuming until Q4. ORDERS-20831 dependency. Assigned: Caleb. | Multum SKG Content Areas Priority List; 26Q3 Priorities
14 | Three Drug Images | RX-2667 | 26.Q1 / 26.Q2 | Complete | In Progress | Images migrating. Automation of daily VA CMOP image updates in progress. Assigned: Sai. | Complete | EHRC API live. | Multum SKG Content Areas Priority List
15 | Remaining Global Distribute - MedGuide | RX-2768 | 26.Q3 | Not Started | Not Started | MedGuide content not yet in SKG. | Not Started | New EHRC MedGuide API required. Contract below RX-2113. Assigned: Minakshi. | Multum SKG Content Areas Priority List; 26Q3 Priorities
15 | Remaining Global Distribute - Labels | RX-2768 | 26.Q3 / 26.Q4 | Not Started | Not Started | Labels content not yet in SKG. | Not Started | New EHRC Labels API required. Contract TBD with Aimee. Assigned: Minakshi. | Multum SKG Content Areas Priority List; 26Q3 Priorities
15 | Remaining Global Distribute - Manufacturer Ordered Drug Names | RX-2768 | 26.Q3 | Not Started | Not Started | Not yet in SKG. | Not Required |  | Multum SKG Content Areas Priority List
16 | Medication Order Sentences | RX-9208 | 26.Q3 | Not Started | Not Started | Not yet in SKG. No consumers yet in Q3. | Not Required | No API defined. No consumers yet. | Multum SKG Content Areas Priority List; 26Q3 Priorities
17 | Automate Content Deployment to SKG | RX-8927 | 26.Q3 | In Progress | In Progress | Manual TTL deployment weekly as interim. Raghu team owns automation. Assigned: Madhulika/Sai. | N/A | Infrastructure effort, not a content API. | 26Q3 Priorities